## Releases
Number | Project | Release Jira | Release Excel | Remarks | Ttus | Dev. Trt | Dev. End | KW Dev. Trt | KW Dev. End | Effort Server | Effort Client | Effort App | Effort Web | Effort Testteam | Estimates Satus | Developer Server | Developer Client | Developer App | Developer Web | Tester
2020-001 | IT | 1.0.2.0 | kein RE | Data corrections | In Bugfixing | 2020-01-01 | 2020-03-18 | 1 | 12 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-002 | JORA | 1.5.0.0 | kein RE | Live Cycle Release | Released | 2020-02-01 | 2020-04-01 | 5 | 14 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-003 | Interlaken | 1.1.2.0 | kein RE | Spring release | Waiting | 2020-03-01 | 2020-04-01 | 10 | 14 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-004 | ORMA | 5.3.4.0 | Link | Performance Release | Released | 2020-03-01 | 2020-04-23 | 10 | 17 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-005 | PO Geko/KISS | 0.9.3.0 | Link | Project release | Released | 2020-04-01 | 2020-04-27 | 14 | 18 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-006 | NPA | 1.3.0.0 | kein RE | Autumn release | Released | 2020-04-01 | 2020-04-28 | 14 | 18 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-007 | VATRO | 1.4.2.0 | kein RE | Service Release | Released | 2020-04-22 | 2020-05-01 | 17 | 18 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-008 | IT | 1.0.4.0 | Link | Spring release | Released | 2020-02-01 | 2020-05-01 | 5 | 18 | [6 empty] | 2 | 2 | 0 | 0 | 0.2
2020-009 | IT | 1.0.4.0 - Scanclient | Link | Spring release | Released | 2020-02-01 | 2020-05-01 | 5 | 18 | [6 empty] | 0 | 1 | 0 | 0 | 0.2
2020-010 | FOR | 0.9.2 | Link | Project release | Released | 2020-04-01 | 2020-05-08 | 14 | 19 | [6 empty] | 1 | 2 | 0 | 1 | 0.2
2020-012 | PO für TPO | 0.8.0.0 | Link | Project release | Released | 2020-04-01 | 2020-05-20 | 14 | 21 | [6 empty] | 1 | 2 | 0 | 0 | 0.2
2020-013 | VI | 0.8.3.0 | Link | Project release | Released | 2020-04-20 | 2020-05-29 | 17 | 22 | [6 empty] | 1 | 3 | 0 | 1 | 0.2
2020-017 | ORMA - Geko | 5.9.1.0 a | Link | Projektrelease (Iteration 1) | Released | 2020-05-14 | 2020-06-27 | 20 | 26 | 336 | 208 |  |  |  | FINALE | 1 | 1 | 0 | 0 | 0.2
2020-015 | PO Geko/KISS | 0.9.4.0 | Link | Project release | Released | 2020-05-25 | 2020-07-01 | 22 | 27 | 480 | 360 |  |  |  | FINALE | 4 | 4 | 0 | 0 | 0.2
2020-045 | PO für MP | 0.9.0.0 | kein RE | Adaption Produkt | Released | 2020-06-08 | 2020-07-01 | 24 | 27 | [6 empty] | 1 | 2 | 0 | 0 | 0.2
2020-018 | T | 0.8.1.0 | Link | Project release | Released | 2020-05-18 | 2020-07-21 | 21 | 30 | 21.5 | 34 |  |  |  | PROV | 1 | 2 | 0 | 0 | 0.2
2020-059 | JTI/USP | JTI/USP | kein RE | JTI/USP | Released | 2020-06-15 | 2020-07-22 | 25 | 30 | [5 empty] | KEINE EST
2020-057 | ORMA | 5.3.5.0 | Link | Clean ORMA Release | Released | 2020-06-16 | 2020-07-23 | 25 | 30 | 80 | 80 |  |  |  | FINALE | 1 | 1 | 0 | 0 | 0.2
2020-056 | PO Geko/KISS | 0.9.5.0 | Link | Project release | Released | 2020-07-02 | 2020-07-27 | 27 | 31 | 480 | 360 |  |  |  | PROV | 4 | 4 | 0 | 0 | 0.2
2020-026 | IT | 1.0.6.0 | Link | Baucontrol, Meldewesen | Released | 2020-07-20 | 2020-08-10 | 30 | 33 | 460 | 172 |  |  |  | FINALE | 2 | 1 | 0 | 0 | 0.2
2020-014 | PO | 1.5.3.0 | kein RE | Performance Release | Released | 2020-05-15 | 2020-08-12 | 20 | 33 | [6 empty] | 1 | 1 | 0 | 0 | 0.2
2020-022 | Opus | 1.3.3.0 | kein RE | Handover of operations | In Bugfixing | 2020-04-01 | 2020-08-17 | 14 | 34 | [6 empty] | 1 | 1 | 0 | 0 | 0.2
2020-050 | ORMA - Geko | 5.9.1.0 b | kein RE | Daten anonymisierung | Released | 2020-05-14 | 2020-08-17 | 20 | 34 | 160 |  |  |  |  | FINALE | 1 | 0 | 0 | 0 | 0.2
2020-058 | ORMA | 5.3.5.1 |  | Clean ORMA Release | Released | 2020-07-11 | 2020-08-18 | 28 | 34 | 40 | 40 |  |  |  | FINALE | 1 | 1 | 0 | 0 | 0.2
2020-023 | VI | 0.9.0.0 | Link | Project release | Released | 2020-06-15 | 2020-08-28 | 25 | 35 | [5 empty] | KEINE EST | 4 | 4 | 0 | 1 | 0.2
2020-046 | PO für MP | AP3 |  | Datenmigration | Recorded | 2020-06-08 | 2020-08-28 | 24 | 35 | [6 empty] | 2 | 0 | 0 | 0 | 0.2
2020-047 | PO für MP | AP4 |  | Spezialfunktionen | Recorded | 2020-06-08 | 2020-08-28 | 24 | 35 | [6 empty] | 1 | 1 | 0 | 0 | 0.2
2020-024 | FORMS 2.0 | 1.8.2.0 |  | Project release | Recorded | 2020-07-01 | 2020-08-31 | 27 | 36 | [6 empty] | 0 | 0 | 0 | 0 | 0.2
2020-051 | IT | 1.0.7.0 | Link | Baucontrol, Meldewesen | Released | 2020-07-18 | 2020-08-31 | 29 | 36 | 460 | 172 |  |  |  | FINALE | 2 | 1 | 0 | 0 | 0.2
2020-019 | FORMS 2.0 | 1.8.1.0 |  | Project release | Recorded | 2020-08-01 | 2020-09-01 | 31 | 36 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-064 | IT | 1.0.4.1 |  | Service Release | Released | 2020-08-10 | 2020-09-02 | 33 | 36
2020-071 | NPA | 1.3.1.0 |  | Service Release | Released | 2020-08-24 | 2020-09-02 | 35 | 36
2020-060 | FOR | 0.9.3.0 | Link | Performance Release | Released | 2020-07-11 | 2020-09-03 | 28 | 36 | 30 | 41 |  |  |  | PROV | 1 | 1 | 0 | 0 | 0
2020-065 | PO für MP | 0.9.0.0+ |  | Create Tool for anonymization of Database | Released | 2020-08-17 | 2020-09-04 | 34 | 36
2020-055 | Duplex | 1.4 |  | Duplex | In Bugfixing | 2020-08-10 | 2020-09-07 | 33 | 37 | [6 empty] | 0 | 1 | 0 | 0 | 0
2020-042 | PO für TPO | 0.8.1 - MVP+ (PR1) |  | Dataobjects Journal | Released | 2020-08-31 | 2020-09-11 | 36 | 37 | [6 empty] | 2 | 2 | 0 | 0 | 0.2
2020-062 | PO für MP | 0.9.1.0 |  | Correct delivery | Released | 2020-08-01 | 2020-09-11 | 31 | 37
2020-067 | IT | 1.0.4.2 |  | DFI | In Bugfixing | 2020-08-31 | 2020-09-11 | 36 | 37
2020-021 | ORMA | 5.4.0.0 | Link | Autumn release (EUROPOL) (Iteration 1) | In Bugfixing | 2020-08-25 | 2020-09-14 | 35 | 38 | 576 | 280 |  |  |  | FINALE | 2 | 1 | 0 | 0 | 0.2
2020-061 | KISS | 0.9.6.0 |  | Project release | Released | 2020-08-25 | 2020-09-16 | 35 | 38
2020-011 | FL Recherche | 2.4.2.0 | kein RE | Service Release | In Bugfixing | 2020-09-14 | 2020-09-18 | 38 | 38 | [6 empty] | 2 | 1 | 0 | 0 | 0
2020-029 | T | 0.8.2.0 |  | Project release | In development | 2020-08-10 | 2020-09-29 | 33 | 40 | [6 empty] | 1 | 2 | 0 | 0 | 0.2
2020-048 | PO für MP | 0.9.2.0 |  | Datenmasken, Datenübernahme, Rapportierung (ev. nur bei uns inTllation und erst im 2021 beim FUB) | Recorded | 2020-09-14 | 2020-10-01 | 38 | 40 | [6 empty] | 1 | 1 | 0 | 0 | 0.2
2020-016 | FOR | 0.9.5 | Link | Project release | Planned | 2020-09-14 | 2020-10-02 | 38 | 40 | 150 | 250 |  | 40 |  | FINALE | 1 | 2 | 0 | 1 | 0.2
2020-043 | PO für TPO | 0.8.2 - MVP+ (PR2) |  | ELS Schnittstelle, App Schnittstelle | In development | 2020-09-14 | 2020-10-07 | 38 | 41 |  | 70 |  |  |  | FINALE | 2 | 0 | 0 | 0 | 0.2
2020-033 | VATRO | 1.5.0.0 |  | Autumn release | Planned | 2020-09-14 | 2020-10-08 | 38 | 41 | 200 | 220 |  |  |  |  | 2 | 2 | 0 | 0 | 0.2
2020-052 | IT | 1.0.8.0 |  | Baucontrol, Meldewesen | In Bugfixing | 2020-09-01 | 2020-10-08 | 36 | 41 | [6 empty] | 1 | 1 | 0 | 0 | 0.2
2020-088 | Geko | 0.9.6.0 |  | Project release | Planned | 2020-09-07 | 2020-10-08 | 37 | 41
2020-049 | ESYSP | 2.4.8.1 | kein RE |  | In development | 2020-09-01 | 2020-10-12 | 36 | 42 | [6 empty] | 1 | 1 | 0 | 0 | 0.2
2020-044 | PO für TPO | 0.8.5 - MVP+ |  | MVP+ | Planned | 2020-09-23 | 2020-10-16 | 39 | 42 | [6 empty] | 2 | 2 | 0 | 0 | 0.2
2020-032 | VI | 0.9.1.0 |  | Project release | In development | 2020-09-01 | 2020-10-19 | 36 | 43 | [6 empty] | 2 | 3 | 0 | 1 | 0.2
2020-028 | ORMA | 5.4.0.1 |  | Autumn release (EUROPOL) (Iteration 2) | Planned | 2020-10-06 | 2020-10-25 | 41 | 44 | 144 | 72 |  |  |  | FINALE | 1 | 1 | 0 | 0 | 0.2
2020-034 | FORMS 2.0 | 1.8.3.0 |  | Project release | Recorded | 2020-09-01 | 2020-10-31 | 36 | 44 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-053 | IT | 1.1.0.0 |  | Baucontrol, Meldewesen | Planned | 2020-10-12 | 2020-11-09 | 42 | 46 | [6 empty] | 1 | 1 | 0 | 0 | 0.2
2020-068 | eneXs EES | Sprint 1 |  | Sprint 1 | In development | 2020-09-07 | 2020-11-13 | 37 | 46
2020-072 | NPA | 1.4.0.0 |  | Autumn Release | Recorded | 2020-10-01 | 2020-11-15 | 40 | 47
2020-036 | ORMA - Geko | 5.9.2.0 |  | Projektrelease (Iteration 2) | Planned | 2020-09-25 | 2020-11-16 | 39 | 47 | 560 | 328 |  |  |  | FINALE | 2 | 1 | 0 | 0 | 0.2
2020-084 | KISS | 0.9.7.0 |  | Project release | Planned | 2020-11-01 | 2020-11-24 | 45 | 48
2020-027 | PO | 1.5.4.0 | Link | Unklar ob es benötigt wird | Planned | 2020-10-19 | 2020-11-27 | 43 | 48 | 152 | 176 |  |  |  | FINALE | 1 | 1 | 0 | 0 | 0.2
2020-075 | VATRO | 1.5.1.0 |  | Autumn release 2 | Planned | 2020-10-19 | 2020-11-27 | 43 | 48
2020-066 | ORMA | 5.5.0.0 |  |  | Planned | 2020-11-01 | 2020-11-28 | 45 | 48 | 40 | 40
2020-038 | VI | 0.9.2.0 |  | Project release | Planned | 2020-10-16 | 2020-11-30 | 42 | 49 | [6 empty] | 2 | 3 | 0 | 1 | 0.2
2020-031 | FOR | 1.0.0 |  | Project release | Recorded | 2020-11-16 | 2020-12-01 | 47 | 49 | [6 empty] | 1 | 2 | 0 | 1 | 0.2
2020-089 | Gekio | 0.9.7.0 |  | Project release | Planned | 2020-11-16 | 2020-12-11 | 47 | 50
2020-039 | FORMS 2.0 | 1.9.0.0 |  | Project release | Recorded | 2020-11-01 | 2020-12-31 | 45 | 53 | [6 empty] | 0 | 0 | 0 | 0 | 0
2020-040 | ORMA - Geko | 5.9.3.0 |  | Projektrelease (Iteration 3) mit Volltext | Planned | 2020-12-18 | 2021-01-26 | 51 | 5 | 436 | 40 |  |  |  | FINALE | 2 | 1 | 0 | 0 | 0.2
2020-073 | ORMA | 5.5.0.1 |  |  | Planned | 2020-01-12 | 2021-01-26 | 3 | 5
2020-069 | eneXs EES | Sprint 2 |  | Sprint 2 | Recorded | 2020-11-16 | 2021-01-31 | 47 | 6
2020-077 | VI | 0.9.3.0 |  | Project release | Planned | 2020-12-14 | 2021-02-12 | 51 | 7
2020-041 | T | 0.8.3.0 |  | Project release | Planned | 2020-12-01 | 2021-02-28 | 49 | 10 | [6 empty] | 1 | 2 | 0 | 0 | 0.2
| FORMS 2.0 | 1.9.1.0 |  | Project release | Recorded | 2021-01-01 | 2021-02-28 | 1 | 10
2020-035 | PO | 1.5.5.0 | Link | Improvement Release | Recorded | 2021-02-01 | 2021-03-01 | 6 | 10 | 192 | 288 |  |  |  | FINALE | 1 | 1 | 0 | 0 | 0.2
2020-076 | IT | FR21 |  | With JustControl | Planned | 2021-02-01 | 2021-03-01 | 6 | 10
2020-083 | JUGA | 0.8.3.0 |  | Project release | Planned | 2021-01-01 | 2021-03-01 | 1 | 10
2020-085 | KISS | 0.9.8.0 |  | Project release | Planned | 2021-02-11 | 2021-03-11 | 7 | 11
2020-090 | Geio | 0.9.8.0 |  | Project release | Planned | 2021-02-11 | 2021-03-11 | 7 | 11
| ORMA - Geko | 5.9.4.0 |  | Projektrelease (Iteration 4) | Planned | 2021-02-18 | 2021-03-15 | 8 | 12 | 112 | 112 |  |  |  | FINALE
| eneXs EES | Sprint 3 |  | Sprint 3 | Recorded | 2021-02-01 | 2021-04-02 | 6 | 14
| IT | 1.1.2.0 |  | April Release | Recorded | 2021-03-01 | 2021-04-12 | 10 | 16
2020-078 | VI | 1.0.0.0 |  | Project release Go Live | Planned | 2020-03-01 | 2021-04-15 | 10 | 16
| ORMA - Geko | 5.9.5.0 |  | Projektrelease (Iteration 5) Function complete | Planned | 2021-04-14 | 2021-04-27 | 16 | 18 | 72 | 72 |  |  |  | FINALE
2020-086 | KISS / Geko | 0.9.9.0 |  | Project release | Planned | 2021-04-22 | 2021-04-29 | 17 | 18
| FORMS 2.0 | 2.0.0.0 |  | Project release | Recorded | 2021-03-01 | 2021-04-30 | 10 | 18
2020-087 | KISS / Geko | 1.0.0.0 |  | Project release | Planned | 2021-05-17 | 2021-05-26 | 21 | 22
| VI | 1.0.1.0 |  | Service Release | Recorded | 2021-05-01 | 2021-05-28 | 18 | 22
2020-079 | T | 0.9.0.0 |  | Project release | Planned | 2021-04-01 | 2021-05-31 | 14 | 23
| Juga | 0.8.4.0 |  | Project release | Planned | 2021-04-01 | 2021-05-31 | 14 | 23
| ORMA - Geko | 5.9.6.0 |  | Projektrelease Corrections | Planned | 2021-05-24 | 2021-06-08 | 22 | 24 | 56 | 56 |  |  |  | FINALE
| Vollzug | 0.8.0.0 |  | Project release | Planned | 2021-05-01 | 2021-06-30 | 18 | 27
| FORMS 2.0 | 2.0.1.0 |  | Project release | Recorded | 2021-05-01 | 2021-06-30 | 18 | 27
| ORMA - Geko | 6.0.0.0 |  | Projektrelease Go Live | Planned | 2021-07-12 | 2021-07-27 | 29 | 31 | 56 | 56 |  |  |  | FINALE
2020-080 | T | 0.9.1.0 |  | Project release | Planned | 2021-05-01 | 2021-07-31 | 18 | 31
| Juga | 0.9.0.0 |  | Project release | Planned | 2021-06-01 | 2021-07-31 | 23 | 31
| Vollzug | 0.8.1.0 |  | Project release | Planned | 2021-07-01 | 2021-08-31 | 27 | 36
| IT | HR21 |  | Löwi knows the details | Planned | 2021-06-01 | 2021-09-01
2020-081 | T | 0.9.2.0 |  | Project release | Planned | 2021-08-01 | 2021-09-30 | 32 | 40
| VI | 1.0.2.0 |  | Service Release | Recorded | 2021-08-01 | 2021-09-30 | 32 | 40
| IT | 1.1.3.0 |  | Autumn Release | Recorded | 2021-08-01 | 2021-09-30 | 32 | 40
| Juga | 0.9.1.0 |  | Project release | Planned | 2021-10-01 | 2021-11-30 | 40 | 49
| Vollzug | 0.8.2.0 |  | Project release | Planned | 2021-10-01 | 2021-11-30 | 40 | 49
2020-082 | T | 1.0.0.0 |  | Project release | Planned | 2022-01-01 | 2022-02-28 | 1 | 10
| VI | 1.0.3.0 |  | Service Release | Recorded | 2021-12-01 | 2022-02-28 | 49 | 10
| Juga | 0.9.2.0 |  | Project release | Planned | 2022-01-01 | 2022-02-28 | 1 | 10
| Vollzug | 0.8.3.0 |  | Project release | Planned | 2022-01-01 | 2022-02-28 | 1 | 10
| T | 1.0.1.0 |  | Project release | Recorded | 2022-03-01 | 2022-03-31 | 10 | 14
| Vollzug | 0.8.4.0 |  | Project release | Planned | 2022-03-01 | 2022-04-30 | 10 | 18
| Juga | 1.0.0.0 |  | Project release | Planned | 2022-04-01 | 2022-05-31 | 14 | 23
| IT | 1.1.4.0 |  | Spring release | Recorded | 2022-04-18 | 2022-05-31 | 17 | 23
| Juga | 1.0.1.0 |  | Project release | Planned | 2022-05-01 | 2022-06-30 | 19 | 27
| Vollzug | 0.9.0.0 |  | Project release | Planned | 2022-05-01 | 2022-06-30 | 19 | 27
| VI | 1.0.4.0 |  | Service Release | Recorded | 2022-07-01 | 2022-08-31 | 27 | 36
| Vollzug | 0.9.1.0 |  | Project release | Planned | 2022-07-01 | 2022-08-31 | 27 | 36
| T | 1.0.2.0 |  | Project release | Recorded | 2022-08-01 | 2022-09-30 | 32 | 40
| Juga | 1.0.2.0 |  | Project release | Planned | 2022-08-01 | 2022-09-30 | 32 | 40
| Vollzug | 0.9.2.0 |  | Project release | Planned | 2022-09-01 | 2022-10-31 | 36 | 45
| VI | 1.0.5.0 |  | Service Release | Recorded | 2022-12-01 | 2023-02-28 | 49 | 9
| Vollzug | 1.0.0.0 |  | Project release | Planned | 2023-01-01 | 2023-02-28 | 1 | 9
| Vollzug | 1.0.1.0 |  | Project release | Planned | 2023-02-01 | 2023-03-31 | 5 | 13
| Vollzug | 1.0.2.0 |  | Project release | Planned | 2023-02-01 | 2023-03-31 | 5 | 13
| T | 1.1.0.0 |  | Spring release | Recorded | 2022-03-01 | 2023-04-30 | 10 | 18
| Juga | 1.1.0.0 |  | Spring release | Planned | 2022-03-01 | 2023-04-30 | 10 | 18
| IT | 1.1.5.0 |  | Spring release | Recorded | 2023-04-17 | 2023-05-31 | 16 | 22
| VI | 1.1.0.0 |  | Autum Release | Recorded | 2023-10-01 | 2023-11-30 | 40 | 48
| Vollzug | 1.1.0.0 |  | Autumn release | Planned | 2023-10-01 | 2023-11-30 | 40 | 48
Formulas:
KW Dev. Trt = WEEKNUM([Dev. Trt])
KW Dev. End = WEEKNUM([Dev. End])

## Overview 2020
Number | Customer | Project | Release | Status |  | KW Dev. Start | KW Dev. End | KW Bug. Start | KW Bug. End | 2020-09-07 11:34 | 2020-09-14 11:34 | 2020-09-21 11:34 | 2020-09-28 11:34 | 2020-10-05 11:34 | 2020-10-12 11:34 | 2020-10-19 11:34 | 2020-10-26 11:34 | 2020-11-02 11:34 | 2020-11-09 11:34 | 2020-11-16 11:34 | 2020-11-23 11:34 | 2020-11-30 11:34 | 2020-12-07 11:34 | 2020-12-14 11:34 | 2020-12-21 11:34 | 2020-12-28 11:34 | 2021-01-04 11:34 | 2021-01-11 11:34 | 2021-01-18 11:34
[5 empty] | Fertigstellung Jahr |  |  |  |  | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 2 | 3 | 4
2020-040 | ORMA - Geko | 5.9.3.0 | 0 | 44183 | 1900-02-19 | 5 | 436 | 437 | 438
2020-073 | ORMA | 5.5.0.1 | 0 | 43842 | 1900-01-02 | 5 | 0 | 1 | 2
2020-069 | eneXs EES | Sprint 2 | 0 | 44151 | 1900-02-15 | 6 | 0 | 1 | 2
2020-077 | VI | 0.9.3.0 | 0 | 44179 | 1900-02-19 | 7 | 0 | 1 | 2
2020-035 | PO | 1.5.5.0 | Link | 44228 | 1900-01-05 | 10 | 192 | 193 | 194
2020-041 | T | 0.8.3.0 | 0 | 44166 | 1900-02-17 | 10 | 0 | 1 | 2
2020-076 | IT | FR21 | 0 | 44228 | 1900-01-05 | 10 | 0 | 1 | 2
2020-082 | T | 1.0.0.0 | 0 | 44562 | 1899-12-31 | 10 | 0 | 1 | 2
2020-083 | JUGA | 0.8.3.0 | 0 | 44197 | 1899-12-31 | 10 | 0 | 1 | 2
2020-085 | KISS | 0.9.8.0 | 0 | 44238 | 1900-01-06 | 11 | 0 | 1 | 2
2020-090 | Geio | 0.9.8.0 | 0 | 44238 | 1900-01-06 | 11 | 0 | 1 | 2
2020-001 | IT | 1.0.2.0 | kein RE | 43831 | 1899-12-31 | 12 | 0 | 1 | 2
2020-002 | JORA | 1.5.0.0 | kein RE | 43862 | 1900-01-04 | 14 | 0 | 1 | 2
2020-003 | Interlaken | 1.1.2.0 | kein RE | 43891 | 1900-01-09 | 14 | 0 | 1 | 2
2020-078 | VI | 1.0.0.0 | 0 | 43891 | 1900-01-09 | 16 | 0 | 1 | 2
2020-004 | ORMA | 5.3.4.0 | Link | 43891 | 1900-01-09 | 17 | 0 | 1 | 2
2020-005 | PO Geko/KISS | 0.9.3.0 | Link | 43922 | 1900-01-13 | 18 | 0 | 1 | 2
2020-006 | NPA | 1.3.0.0 | kein RE | 43922 | 1900-01-13 | 18 | 0 | 1 | 2
2020-007 | VATRO | 1.4.2.0 | kein RE | 43943 | 1900-01-16 | 18 | 0 | 1 | 2
2020-008 | IT | 1.0.4.0 | Link | 43862 | 1900-01-04 | 18 | 0 | 1 | 2
2020-009 | IT | 1.0.4.0 - Scanclient | Link | 43862 | 1900-01-04 | 18 | 0 | 1 | 2
2020-086 | KISS / Geko | 0.9.9.0 | 0 | 44308 | 1900-01-16 | 18 | 0 | 1 | 2
2020-010 | FOR | 0.9.2 | Link | 43922 | 1900-01-13 | 19 | 0 | 1 | 2
2020-012 | PO für TPO | 0.8.0.0 | Link | 43922 | 1900-01-13 | 21 | 0 | 1 | 2
2020-013 | VI | 0.8.3.0 | Link | 43941 | 1900-01-16 | 22 | 0 | 1 | 2
2020-087 | KISS / Geko | 1.0.0.0 | 0 | 44333 | 1900-01-20 | 22 | 0 | 1 | 2
2020-079 | T | 0.9.0.0 | 0 | 44287 | 1900-01-13 | 23 | 0 | 1 | 2
2020-017 | ORMA - Geko | 5.9.1.0 a | Link | 43965 | 1900-01-19 | 26 | 336 | 337 | 338
2020-015 | PO Geko/KISS | 0.9.4.0 | Link | 43976 | 1900-01-21 | 27 | 480 | 481 | 482
2020-045 | PO für MP | 0.9.0.0 | kein RE | 43990 | 1900-01-23 | 27 | 0 | 1 | 2
2020-018 | T | 0.8.1.0 | Link | 43969 | 1900-01-20 | 30 | 21.5 | 22.5 | 23.5
2020-057 | ORMA | 5.3.5.0 | Link | 43998 | 1900-01-24 | 30 | 80 | 81 | 82
2020-059 | JTI/USP | JTI/USP | kein RE | 43997 | 1900-01-24 | 30 | 0 | 1 | 2
2020-056 | PO Geko/KISS | 0.9.5.0 | Link | 44014 | 1900-01-26 | 31 | 480 | 481 | 482
2020-080 | T | 0.9.1.0 | 0 | 44317 | 1900-01-17 | 31 | 0 | 1 | 2
2020-014 | PO | 1.5.3.0 | kein RE | 43966 | 1900-01-19 | 33 | 0 | 1 | 2
2020-026 | IT | 1.0.6.0 | Link | 44032 | 1900-01-29 | 33 | 460 | 461 | 462
2020-022 | Opus | 1.3.3.0 | kein RE | 43922 | 1900-01-13 | 34 | 0 | 1 | 2
2020-050 | ORMA - Geko | 5.9.1.0 b | kein RE | 43965 | 1900-01-19 | 34 | 160 | 161 | 162
2020-058 | ORMA | 5.3.5.1 | 0 | 44023 | 1900-01-27 | 34 | 40 | 41 | 42
2020-023 | VI | 0.9.0.0 | Link | 43997 | 1900-01-24 | 35 | 0 | 1 | 2
2020-046 | PO für MP | AP3 | 0 | 43990 | 1900-01-23 | 35 | 0 | 1 | 2
2020-047 | PO für MP | AP4 | 0 | 43990 | 1900-01-23 | 35 | 0 | 1 | 2
2020-019 | FORMS 2.0 | 1.8.1.0 | 0 | 44044 | 1900-01-30 | 36 | 0 | 1 | 2
2020-024 | FORMS 2.0 | 1.8.2.0 | 0 | 44013 | 1900-01-26 | 36 | 0 | 1 | 2
2020-051 | IT | 1.0.7.0 | Link | 44030 | 1900-01-28 | 36 | 460 | 461 | 462
2020-060 | FOR | 0.9.3.0 | Link | 44023 | 1900-01-27 | 36 | 30 | 31 | 32
2020-064 | IT | 1.0.4.1 | 0 | 44053 | 1900-02-01 | 36 | 0 | 1 | 2
2020-065 | PO für MP | 0.9.0.0+ | 0 | 44060 | 1900-02-02 | 36 | 0 | 1 | 2
2020-071 | NPA | 1.3.1.0 | 0 | 44067 | 1900-02-03 | 36 | 0 | 1 | 2
2020-042 | PO für TPO | 0.8.1 - MVP+ (PR1) | 0 | 44074 | 1900-02-04 | 37 | 0 | 1 | 2
2020-055 | Duplex | 1.4 | 0 | 44053 | 1900-02-01 | 37 | 0 | 1 | 2
2020-062 | PO für MP | 0.9.1.0 | 0 | 44044 | 1900-01-30 | 37 | 0 | 1 | 2
2020-067 | IT | 1.0.4.2 | 0 | 44074 | 1900-02-04 | 37 | 0 | 1 | 2
2020-011 | FL Recherche | 2.4.2.0 | kein RE | 44088 | 1900-02-06 | 38 | 0 | 1 | 2
2020-021 | ORMA | 5.4.0.0 | Link | 44068 | 1900-02-03 | 38 | 576 | 577 | 578
2020-061 | KISS | 0.9.6.0 | 0 | 44068 | 1900-02-03 | 38 | 0 | 1 | 2
2020-016 | FOR | 0.9.5 | Link | 44088 | 1900-02-06 | 40 | 150 | 151 | 152
2020-029 | T | 0.8.2.0 | 0 | 44053 | 1900-02-01 | 40 | 0 | 1 | 2
2020-048 | PO für MP | 0.9.2.0 | 0 | 44088 | 1900-02-06 | 40 | 0 | 1 | 2
2020-081 | T | 0.9.2.0 | 0 | 44409 | 1900-01-31 | 40 | 0 | 1 | 2
2020-033 | VATRO | 1.5.0.0 | 0 | 44088 | 1900-02-06 | 41 | 200 | 201 | 202
2020-043 | PO für TPO | 0.8.2 - MVP+ (PR2) | 0 | 44088 | 1900-02-06 | 41 | 0 | 1 | 2
2020-052 | IT | 1.0.8.0 | 0 | 44075 | 1900-02-04 | 41 | 0 | 1 | 2
2020-088 | Geko | 0.9.6.0 | 0 | 44081 | 1900-02-05 | 41 | 0 | 1 | 2
2020-044 | PO für TPO | 0.8.5 - MVP+ | 0 | 44097 | 1900-02-07 | 42 | 0 | 1 | 2
2020-049 | ESYSP | 2.4.8.1 | kein RE | 44075 | 1900-02-04 | 42 | 0 | 1 | 2
2020-032 | VI | 0.9.1.0 | 0 | 44075 | 1900-02-04 | 43 | 0 | 1 | 2
2020-028 | ORMA | 5.4.0.1 | 0 | 44110 | 1900-02-09 | 44 | 144 | 145 | 146
2020-034 | FORMS 2.0 | 1.8.3.0 | 0 | 44075 | 1900-02-04 | 44 | 0 | 1 | 2
2020-053 | IT | 1.1.0.0 | 0 | 44116 | 1900-02-10 | 46 | 0 | 1 | 2
2020-068 | eneXs EES | Sprint 1 | 0 | 44081 | 1900-02-05 | 46 | 0 | 1 | 2
2020-036 | ORMA - Geko | 5.9.2.0 | 0 | 44099 | 1900-02-07 | 47 | 560 | 561 | 562
2020-072 | NPA | 1.4.0.0 | 0 | 44105 | 1900-02-08 | 47 | 0 | 1 | 2
2020-027 | PO | 1.5.4.0 | Link | 44123 | 1900-02-11 | 48 | 152 | 153 | 154
2020-066 | ORMA | 5.5.0.0 | 0 | 44136 | 1900-02-13 | 48 | 40 | 41 | 42
2020-075 | VATRO | 1.5.1.0 | 0 | 44123 | 1900-02-11 | 48 | 0 | 1 | 2
2020-084 | KISS | 0.9.7.0 | 0 | 44136 | 1900-02-13 | 48 | 0 | 1 | 2
2020-031 | FOR | 1.0.0 | 0 | 44151 | 1900-02-15 | 49 | 0 | 1 | 2
2020-038 | VI | 0.9.2.0 | 0 | 44120 | 1900-02-10 | 49 | 0 | 1 | 2
2020-089 | Gekio | 0.9.7.0 | 0 | 44151 | 1900-02-15 | 50 | 0 | 1 | 2
2020-039 | FORMS 2.0 | 1.9.0.0 | 0 | 44136 | 1900-02-13 | 53 | 0 | 1 | 2

## Conf (hidden)
CURRENTDATE | 2020-10-09 11:34
STARTDATE | 2020-10-05 11:34
STATUS | Recorded | Planned | In development | In Bugfixing | Released | Waiting
CURRENT CAL. WEEK | 41
ESTIMATE STATUS | KEINE EST | PROV | FINALE

## Ressource plan (hidden)
[15 empty] | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester | Dev Server | Dev Client | Dev App | Dev Web | Tester
[15 empty] | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
[11 empty] | Auslastung | [83 empty] | 13 | 14 | 3 | 1 | 1.8 | 12 | 13 | 3 | 1 | 1.6 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 6 | 8 | 3 | 1 | 1.2 | 5 | 8 | 3 | 1 | 1 | 5 | 8 | 3 | 1 | 1 | 5 | 8 | 3 | 1 | 0.8 | 5 | 8 | 3 | 1 | 0.8 | 3 | 7 | 3 | 1 | 0.6 | 3 | 7 | 3 | 1 | 0.6 | 2 | 5 | 3 | 0 | 0.4 | 2 | 5 | 3 | 0 | 0.4 | 2 | 5 | 3 | 0 | 0.4 | 2 | 5 | 3 | 0 | 0.4 | 1 | 4 | 3 | 0 | 0.2 | 1 | 4 | 3 | 0 | 0.2 | 1 | 4 | 3 | 0 | 0.2 | -1 | 3 | 3 | 0 | 0 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2
Number | Customer | Project | Release | Status | KW Dev. Start | KW Dev. End | KW Bug. Start | KW Bug. End | Status Index | Dev Server | Dev Client | Dev App | Dev Web | Tester | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 53 | 53 | 53 | 53 | 53
2020-001 | IT | 1.0.2.0 | kein RE | 43831 | 12 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0
2020-003 | Interlaken | 1.1.2.0 | kein RE | 43891 | 14 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0
2020-002 | JORA | 1.5.0.0 | kein RE | 43862 | 14 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0
2020-004 | ORMA | 5.3.4.0 | Link | 43891 | 17 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0
2020-005 | PO Geko/KISS | 0.9.3.0 | Link | 43922 | 18 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0
2020-006 | NPA | 1.3.0.0 | kein RE | 43922 | 18 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0
2020-007 | VATRO | 1.4.2.0 | kein RE | 43943 | 18 | 0 | 1 | 2 |  | 2 | 2 | 0 | 0 | 0.2
2020-008 | IT | 1.0.4.0 | Link | 43862 | 18 | 0 | 1 | 2 |  | 0 | 1 | 0 | 0 | 0.2
2020-009 | IT | 1.0.4.0 - Scanclient | Link | 43862 | 18 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0
2020-010 | FOR | 0.9.2 | Link | 43922 | 19 | 0 | 1 | 2 |  | 1 | 2 | 0 | 1 | 0.2
2020-011 | FL Recherche | 2.4.2.0 | kein RE | 44088 | 38 | 0 | 1 | 2 |  | 2 | 1 | 0 | 0 | 0
2020-012 | PO für TPO | 0.8.0.0 | Link | 43922 | 21 | 0 | 1 | 2 |  | 1 | 2 | 0 | 0 | 0.2
2020-013 | VI | 0.8.3.0 | Link | 43941 | 22 | 0 | 1 | 2 |  | 1 | 3 | 0 | 1 | 0.2
2020-014 | PO | 1.5.3.0 | kein RE | 43966 | 33 | 0 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0.2
2020-015 | PO Geko/KISS | 0.9.4.0 | Link | 43976 | 27 | 480 | 481 | 482 |  | 4 | 4 | 0 | 0 | 0.2 | [90 empty] | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2 | 4 | 4 | 0 | 0 | 0.2
2020-049 | ESYSP | 2.4.8.1 | kein RE | 44075 | 42 | 0 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0.2
2020-022 | Opus | 1.3.3.0 | kein RE | 43922 | 34 | 0 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0.2
2020-016 | FOR | 0.9.5 | Link | 44088 | 40 | 150 | 151 | 152 |  | 1 | 2 | 0 | 1 | 0.2 | 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2; 1: 1; 2: 2; 3: 0; 4: 1; 5: 0.2
2020-045 | PO für MP | 0.9.0.0 | kein RE | 43990 | 27 | 0 | 1 | 2 |  | 1 | 2 | 0 | 0 | 0.2
2020-017 | ORMA - Geko | 5.9.1.0 a | Link | 43965 | 26 | 336 | 337 | 338 |  | 1 | 1 | 0 | 0 | 0.2 | [85 empty] | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2
2020-050 | ORMA - Geko | 5.9.1.0 b | kein RE | 43965 | 34 | 160 | 161 | 162 |  | 1 | 0 | 0 | 0 | 0.2 | 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 0; 3: 0; 4: 0; 5: 0.2
2020-018 | T | 0.8.1.0 | Link | 43969 | 30 | 21.5 | 22.5 | 23.5 |  | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0
2020-019 | FORMS 2.0 | 1.8.1.0 | 0 | 44044 | 36 | 0 | 1 | 2 |  | 1 | 2 | 0 | 0 | 0.2
2020-055 | Duplex | 1.4 | 0 | 44053 | 37 | 0 | 1 | 2 |  | 0 | 1 | 0 | 0 | 0
2020-026 | IT | 1.0.6.0 | Link | 44032 | 33 | 460 | 461 | 462 |  | 2 | 1 | 0 | 0 | 0.2 | 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2
2020-021 | ORMA | 5.4.0.0 | Link | 44068 | 38 | 576 | 577 | 578 |  | 2 | 1 | 0 | 0 | 0.2 | 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2
2020-042 | PO für TPO | 0.8.1 - MVP+ (PR1) | 0 | 44074 | 37 | 0 | 1 | 2 |  | 2 | 2 | 0 | 0 | 0.2
2020-043 | PO für TPO | 0.8.2 - MVP+ (PR2) | 0 | 44088 | 41 | 0 | 1 | 2 |  | 2 | 0 | 0 | 0 | 0.2
2020-023 | VI | 0.9.0.0 | Link | 43997 | 35 | 0 | 1 | 2 |  | 2 | 0 | 0 | 0 | 0.2
2020-046 | PO für MP | AP3 | 0 | 43990 | 35 | 0 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0.2
2020-047 | PO für MP | AP4 | 0 | 43990 | 35 | 0 | 1 | 2 |  | 4 | 4 | 0 | 1 | 0.2
2020-051 | IT | 1.0.7.0 | Link | 44030 | 36 | 460 | 461 | 462 |  | 0 | 0 | 0 | 0 | 0.2 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0.2
2020-024 | FORMS 2.0 | 1.8.2.0 | 0 | 44013 | 36 | 0 | 1 | 2 |  | 2 | 1 | 0 | 0 | 0.2
2020-027 | PO | 1.5.4.0 | Link | 44123 | 48 | 152 | 153 | 154 |  | 1 | 1 | 0 | 0 | 0.2 | 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2
2020-028 | ORMA | 5.4.0.1 | 0 | 44110 | 44 | 144 | 145 | 146 |  | 1 | 1 | 0 | 0 | 0.2 | 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 1; 2: 1; 3: 0; 4: 0; 5: 0.2
2020-029 | T | 0.8.2.0 | 0 | 44053 | 40 | 0 | 1 | 2 |  | 1 | 2 | 0 | 0 | 0.2
2020-031 | FOR | 1.0.0 | 0 | 44151 | 49 | 0 | 1 | 2 |  | 1 | 2 | 0 | 1 | 0.2
2020-032 | VI | 0.9.1.0 | 0 | 44075 | 43 | 0 | 1 | 2 |  | 2 | 3 | 0 | 1 | 0.2
2020-048 | PO für MP | 0.9.2.0 | 0 | 44088 | 40 | 0 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0.2
2020-052 | IT | 1.0.8.0 | 0 | 44075 | 41 | 0 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0.2
2020-044 | PO für TPO | 0.8.5 - MVP+ | 0 | 44097 | 42 | 0 | 1 | 2 |  | 2 | 2 | 0 | 0 | 0.2
2020-033 | VATRO | 1.5.0.0 | 0 | 44088 | 41 | 200 | 201 | 202 |  | 0 | 0 | 0 | 0 | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 1: 0; 2: 0; 3: 0; 4: 0; 5: 0
2020-034 | FORMS 2.0 | 1.8.3.0 | 0 | 44075 | 44 | 0 | 1 | 2 |  | 2 | 2 | 0 | 0 | 0.2
2020-035 | PO | 1.5.5.0 | Link | 44228 | 10 | 192 | 193 | 194 |  | 1 | 1 | 0 | 0 | 0.2 | [5 empty] | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2 | 1 | 1 | 0 | 0 | 0.2
2020-036 | ORMA - Geko | 5.9.2.0 | 0 | 44099 | 47 | 560 | 561 | 562 |  | 2 | 1 | 0 | 0 | 0.2 | 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2; 1: 2; 2: 1; 3: 0; 4: 0; 5: 0.2
2020-053 | IT | 1.1.0.0 | 0 | 44116 | 46 | 0 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0.2
2020-038 | VI | 0.9.2.0 | 0 | 44120 | 49 | 0 | 1 | 2 |  | 2 | 3 | 0 | 1 | 0.2
2020-040 | ORMA - Geko | 5.9.3.0 | 0 | 44183 | 5 | 436 | 437 | 438 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-041 | T | 0.8.3.0 | 0 | 44166 | 10 | 0 | 1 | 2 |  | 1 | 2 | 0 | 0 | 0.2
2020-039 | FORMS 2.0 | 1.9.0.0 | 0 | 44136 | 53 | 0 | 1 | 2 |  | 2 | 1 | 0 | 0 | 0.2
[14 empty] | IST | [80 empty] | 1 | 1 | 0 | 0 | 0.2 | 2 | 2 | 0 | 0 | 0.4 | 6 | 6 | 0 | 0 | 0.6 | 6 | 6 | 0 | 0 | 0.6 | 6 | 6 | 0 | 0 | 0.6 | 6 | 6 | 0 | 0 | 0.6 | 6 | 6 | 0 | 0 | 0.6 | 6 | 6 | 0 | 0 | 0.6 | 8 | 7 | 0 | 0 | 0.8 | 9 | 7 | 0 | 0 | 1 | 9 | 7 | 0 | 0 | 1 | 9 | 7 | 0 | 0 | 1.2 | 9 | 7 | 0 | 0 | 1.2 | 11 | 8 | 0 | 0 | 1.4 | 11 | 8 | 0 | 0 | 1.4 | 12 | 10 | 0 | 1 | 1.6 | 12 | 10 | 0 | 1 | 1.6 | 12 | 10 | 0 | 1 | 1.6 | 12 | 10 | 0 | 1 | 1.6 | 13 | 11 | 0 | 1 | 1.8 | 13 | 11 | 0 | 1 | 1.8 | 13 | 11 | 0 | 1 | 1.8 | 15 | 12 | 0 | 1 | 2 | 16 | 13 | 0 | 1 | 2.2 | 16 | 13 | 0 | 1 | 2.2 | 16 | 13 | 0 | 1 | 2.2 | 16 | 13 | 0 | 1 | 2.2 | 16 | 13 | 0 | 1 | 2.2 | 16 | 13 | 0 | 1 | 2.2
[14 empty] | SOLL | [80 empty] | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2 | 14 | 15 | 3 | 1 | 2
[14 empty] | + / - | [80 empty] | 13 | 14 | 3 | 1 | 1.8 | 12 | 13 | 3 | 1 | 1.6 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 8 | 9 | 3 | 1 | 1.4 | 6 | 8 | 3 | 1 | 1.2 | 5 | 8 | 3 | 1 | 1 | 5 | 8 | 3 | 1 | 1 | 5 | 8 | 3 | 1 | 0.8 | 5 | 8 | 3 | 1 | 0.8 | 3 | 7 | 3 | 1 | 0.6 | 3 | 7 | 3 | 1 | 0.6 | 2 | 5 | 3 | 0 | 0.4 | 2 | 5 | 3 | 0 | 0.4 | 2 | 5 | 3 | 0 | 0.4 | 2 | 5 | 3 | 0 | 0.4 | 1 | 4 | 3 | 0 | 0.2 | 1 | 4 | 3 | 0 | 0.2 | 1 | 4 | 3 | 0 | 0.2 | -1 | 3 | 3 | 0 | 0 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2 | -2 | 2 | 3 | 0 | -0.2

## Overview Tmp (hidden)
Number | Customer | Project | Release | Status | KW Dev. Start | KW Dev. End | KW Bug. Start | KW Bug. End | 2020-09-07 11:34 | 2020-09-14 11:34 | 2020-09-21 11:34 | 2020-09-28 11:34 | 2020-10-05 11:34 | 2020-10-12 11:34 | 2020-10-19 11:34 | 2020-10-26 11:34 | 2020-11-02 11:34 | 2020-11-09 11:34 | 2020-11-16 11:34 | 2020-11-23 11:34 | 2020-11-30 11:34 | 2020-12-07 11:34 | 2020-12-14 11:34 | 2020-12-21 11:34 | 2020-12-28 11:34 | 2021-01-04 11:34 | 2021-01-11 11:34 | 2021-01-18 11:34 | 2021-01-25 11:34 | 2021-02-01 11:34 | 2021-02-08 11:34 | 2021-02-15 11:34
[9 empty] | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 2 | 3 | 4 | 5 | 6 | 7 | 8
2020-014 | PO | 1.5.3.0 | kein RE | 43966 | 33 | 0 | 1 | 2
2020-022 | Opus | 1.3.3.0 | kein RE | 43922 | 34 | 0 | 1 | 2
2020-050 | ORMA - Geko | 5.9.1.0 b | kein RE | 43965 | 34 | 160 | 161 | 162
2020-058 | ORMA | 5.3.5.1 | 0 | 44023 | 34 | 40 | 41 | 42
2020-023 | VI | 0.9.0.0 | Link | 43997 | 35 | 0 | 1 | 2
2020-051 | IT | 1.0.7.0 | Link | 44030 | 36 | 460 | 461 | 462
2020-064 | IT | 1.0.4.1 | 0 | 44053 | 36 | 0 | 1 | 2
2020-065 | PO für MP | 0.9.0.0+ | 0 | 44060 | 36 | 0 | 1 | 2
2020-071 | NPA | 1.3.1.0 | 0 | 44067 | 36 | 0 | 1 | 2
2020-042 | PO für TPO | 0.8.1 - MVP+ (PR1) | 0 | 44074 | 37 | 0 | 1 | 2
2020-055 | Duplex | 1.4 | 0 | 44053 | 37 | 0 | 1 | 2
2020-062 | PO für MP | 0.9.1.0 | 0 | 44044 | 37 | 0 | 1 | 2
2020-067 | IT | 1.0.4.2 | 0 | 44074 | 37 | 0 | 1 | 2
2020-011 | FL Recherche | 2.4.2.0 | kein RE | 44088 | 38 | 0 | 1 | 2
2020-021 | ORMA | 5.4.0.0 | Link | 44068 | 38 | 576 | 577 | 578
2020-027 | PO | 1.5.4.0 | Link | 44123 | 48 | 152 | 153 | 154
2020-061 | KISS | 0.9.6.0 | 0 | 44068 | 38 | 0 | 1 | 2
2020-016 | FOR | 0.9.5 | Link | 44088 | 40 | 150 | 151 | 152
2020-029 | T | 0.8.2.0 | 0 | 44053 | 40 | 0 | 1 | 2
2020-043 | PO für TPO | 0.8.2 - MVP+ (PR2) | 0 | 44088 | 41 | 0 | 1 | 2
2020-033 | VATRO | 1.5.0.0 | 0 | 44088 | 41 | 200 | 201 | 202
2020-052 | IT | 1.0.8.0 | 0 | 44075 | 41 | 0 | 1 | 2
2020-073 | ORMA | 5.5.0.1 | 0 | 43842 | 5 | 0 | 1 | 2
2020-032 | VI | 0.9.1.0 | 0 | 44075 | 43 | 0 | 1 | 2
2020-044 | PO für TPO | 0.8.5 - MVP+ | 0 | 44097 | 42 | 0 | 1 | 2
2020-049 | ESYSP | 2.4.8.1 | kein RE | 44075 | 42 | 0 | 1 | 2
2020-028 | ORMA | 5.4.0.1 | 0 | 44110 | 44 | 144 | 145 | 146
2020-048 | PO für MP | 0.9.2.0 | 0 | 44088 | 40 | 0 | 1 | 2
2020-034 | FORMS 2.0 | 1.8.3.0 | 0 | 44075 | 44 | 0 | 1 | 2
2020-053 | IT | 1.1.0.0 | 0 | 44116 | 46 | 0 | 1 | 2
2020-068 | eneXs EES | Sprint 1 | 0 | 44081 | 46 | 0 | 1 | 2
2020-036 | ORMA - Geko | 5.9.2.0 | 0 | 44099 | 47 | 560 | 561 | 562
2020-072 | NPA | 1.4.0.0 | 0 | 44105 | 47 | 0 | 1 | 2
2020-031 | FOR | 1.0.0 | 0 | 44151 | 49 | 0 | 1 | 2
2020-038 | VI | 0.9.2.0 | 0 | 44120 | 49 | 0 | 1 | 2
2020-035 | PO | 1.5.5.0 | Link | 44228 | 10 | 192 | 193 | 194
2020-039 | FORMS 2.0 | 1.9.0.0 | 0 | 44136 | 53 | 0 | 1 | 2
2020-040 | ORMA - Geko | 5.9.3.0 | 0 | 44183 | 5 | 436 | 437 | 438
2020-041 | T | 0.8.3.0 | 0 | 44166 | 10 | 0 | 1 | 2
2020-066 | ORMA | 5.5.0.0 | 0 | 44136 | 48 | 40 | 41 | 42